## DSM
Design Structure Matrix | [15 empty] | Instructions
X when row depends on column. |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | How to create DSM in Quantum XL
|  | tower fixture SW | Tower intragation test ready | Pen actuator fixture SW | pen actuator integration test ready | pen drive fixture SW | pen drive integration test ready | tower motor selection | pen actuator motor selection | pen drive motor selection | smallest line size selection | vertical pen speed selection | line drawing speed selection | system validation | system integration
1 | tower fixture SW | [14 empty] | Step | Select New DSM from the DSM menu. This will create an empty DSM in a new worksheet. | bar: 1; 10; 12
2 | Tower intragation test ready | [14 empty] | 1 | bar: 1 to 2
3 | Pen actuator fixture SW | bar: 3; 8; 11
4 | pen actuator integration test ready | bar: 3 to 4
5 | pen drive fixture SW | bar: 5; 9; 12
6 | pen drive integration test ready | bar: 5 to 6
7 | tower motor selection | bar: 7
8 | pen actuator motor selection | [14 empty] | Step | Enter task (activity) names in the rows. Columns will be filled automatically. | bar: 8
9 | pen drive motor selection | [14 empty] | 2 | bar: 9
10 | smallest line size selection | bar: 10
11 | vertical pen speed selection | bar: 11
12 | line drawing speed selection | [14 empty] | Step | Put X in the cells for which activity in a row depends on activity in a column. Example: if 'system validation' (#13) depends on 'system integration' (#14), you should put X in intersection for 'system validation' row and 'system integration' column. In this example, put X in cell S18. TIP: Use DSM Navigator (under the DSM menu) to fill the large matrices. | bar: 12
13 | system validation | [14 empty] | 3 | bar: 13 to 14
14 | system integration | bar: 2; 4; 6; 14
[16 empty] | Next Steps… | After you fill the matrix, you can partition DSM using path search algorithm (Sequence DSM) or AEAP and ALAP partitioning methods. Both commands are available under DSM menu.

## Sequenced
DSM (Sequenced - Path Search Algorithm)
X when row depends on column. |  | 7 | 8 | 9 | 10 | 11 | 3 | 4 | 12 | 1 | 2 | 5 | 6 | 14 | 13
|  | tower motor selection | pen actuator motor selection | pen drive motor selection | smallest line size selection | vertical pen speed selection | Pen actuator fixture SW | pen actuator integration test ready | line drawing speed selection | tower fixture SW | Tower intragation test ready | pen drive fixture SW | pen drive integration test ready | system integration | system validation
7 | tower motor selection
8 | pen actuator motor selection
9 | pen drive motor selection
10 | smallest line size selection
11 | vertical pen speed selection
3 | Pen actuator fixture SW |  | x |  |  | x
4 | pen actuator integration test ready | [5 empty] | x
12 | line drawing speed selection
1 | tower fixture SW |  |  |  | x |  |  |  | x
2 | Tower intragation test ready | [8 empty] | x
5 | pen drive fixture SW |  |  | x |  |  |  |  | x
6 | pen drive integration test ready | [10 empty] | x
14 | system integration | [6 empty] | x |  |  | x |  | x
13 | system validation | [12 empty] | X

## ALAP
DSM (As-Late-As-Possible)
X when row depends on column. |  |  | 8 | 9 | 10 | 11 | 12 | 3 | 1 | 5 | 4 | 2 | 6 | 14 | 7 | 13
|  | Level | pen actuator motor selection | pen drive motor selection | smallest line size selection | vertical pen speed selection | line drawing speed selection | Pen actuator fixture SW | tower fixture SW | pen drive fixture SW | pen actuator integration test ready | Tower intragation test ready | pen drive integration test ready | system integration | tower motor selection | system validation
8 | pen actuator motor selection | 1
9 | pen drive motor selection
10 | smallest line size selection
11 | vertical pen speed selection
12 | line drawing speed selection
3 | Pen actuator fixture SW | 2 | x |  |  | x
1 | tower fixture SW |  |  |  | x |  | x
5 | pen drive fixture SW |  |  | x |  |  | x
4 | pen actuator integration test ready | 3 | [5 empty] | x
2 | Tower intragation test ready | [7 empty] | x
6 | pen drive integration test ready | [8 empty] | x
14 | system integration | 4 | [8 empty] | x | x | x
7 | tower motor selection | 5
13 | system validation | [12 empty] | X

## AEAP
|  | User Interface Module |  |  |  | Logic Module |  |  |  | Database Module |  |  |  | APIs for modules |  |  |  |  | Management Module |  |  |  | Doctors Module |  |  |  | Nurses Module |  |  |  | Patience modules
|  | UI for Doctors | UI for Nurses | UI For Management | UI for Patience | Logic for Doctors | Logic for Nurses | Logic for Management | Logic for Patience | DB for Doctors | DB for Nurses | DB for Management | DB for Patience | API for UI Module | API for Logic Module | API for Database Module |  |  | UI For Management | Logic for Management | DB for Management | Documentation | UI for Doctors | Logic for Doctors | DB for Doctors | Documentation | UI for Nurses | Logic for Nurses | DB for Nurses | Documentation | UI for Patience | Logic for Patience | DB for Patience | Documentation | Shared Infrastructure
User Interface Module | UI for Doctors |  | X | X | X | [8 empty] | X | X |  | Management Module | UI For Management |  | X | X
| UI for Nurses | X |  | X | X | [8 empty] | X | X |  |  | Logic for Management | X |  | X
| UI For Management | X | X |  | X | [8 empty] | X | X |  |  | DB for Management | X | X | [14 empty] | X
| UI for Patience | X | X | X | [9 empty] | X | X |  |  | Documentation | X | X | X | [13 empty] | X
Logic Module | Logic for Doctors | [5 empty] | X | X | X |  |  |  |  | X | X | X | Doctors Module | UI for Doctors | [5 empty] | X | X
| Logic for Nurses |  |  |  |  | X |  | X | X |  |  |  |  | X | X | X |  | Logic for Doctors |  |  |  |  | X |  | X
| Logic for Management |  |  |  |  | X | X |  | X |  |  |  |  | X | X | X |  | DB for Doctors |  |  |  |  | X | X | [10 empty] | X
| Logic for Patience |  |  |  |  | X | X | X | [5 empty] | X | X | X |  | Documentation |  |  |  |  | X | X | X | [9 empty] | X
Database Module | DB for Doctors | [9 empty] | X | X | X |  |  | X | Nurses Module | UI for Nurses | [9 empty] | X | X
| DB for Nurses | [8 empty] | X |  | X | X |  |  | X |  | Logic for Nurses | [8 empty] | X |  | X
| DB for Management | [8 empty] | X | X |  | X |  |  | X |  | DB for Nurses | [8 empty] | X | X
| DB for Patience | [8 empty] | X | X | X |  |  |  | X |  | Documentation | [8 empty] | X | X | X
APIs for modules | API for UI Module | [15 empty] | Patience modules | UI for Patience | [13 empty] | X | X
| API for Logic Module | [16 empty] | Logic for Patience | [12 empty] | X |  | X
| API for Database Module | [16 empty] | DB for Patience | [12 empty] | X | X |  |  | X
| Documentations | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  | Documentation | [12 empty] | X | X | X |  | X